## Sheet1
Tasks | 2021 | [6 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024
| Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
Theorithical design of the composition process | bar: 2021 Jun to 2022 Jan
Design of the composition algorithm | bar: 2022 Feb to 2022 Dec
Technical architecture design | bar: 2023 Jan to 2023 Apr
Build a prototype of the composition process | bar: 2023 May to 2023 Sep
Test & Evaluation | bar: 2023 May to 2024 Jan
Review and validate results | bar: 2023 May to 2024 Apr
Write-up
Viva | bar: 2024 Oct